## Ark1
Tidsregistrering af (Navn)
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Gruppekontrakt | business-Process Analyst | 2020-05-11 | 11:20 | 13:30 |  | 2:10 | 2:10
Kravindsamling |  | 2020-05-11 | 13:30 | 14:30 |  | 1:00 | 3:10
Use-case diagram |  | 2020-05-11 | 14:30 | 16:00 |  | 1:30 | 4:40
Furps+ |  | 2020-05-12 | 9:00 | 10:30 |  | 1:30 | 6:10
review af MockUp |  | 2020-05-12 | 10:30 | 11:00 |  | 0:30 | 6:40
Risikoanalyse |  | 2020-05-12 | 11:00 | 14:00 |  | 3:00 | 9:40
Review af Metrikker |  | 2020-05-12 | 14:00 | 14:30 |  | 0:30 | 10:10
Fællesgennemgang af projektplan |  | 2020-05-12 | 14:30 | 16:30 |  | 2:00 | 12:10
UC01 med EMIL |  | 2020-05-13 | 9:00 | 9:30 |  | 0:30 | 12:40
Review af UC02 med Emil |  | 2020-05-13 | 9:30 | 10:00 |  | 0:30 | 13:10
AD01 med Toke |  | 2020-05-13 | 10:00 | 10:30 |  | 0:30 | 13:40
review af AD02 |  | 2020-05-13 | 10:30 | 11:00 |  | 0:30 | 14:10
DOM01 med MIK |  | 2020-05-13 | 11:00 | 11:30 |  | 0:30 | 14:40
Review af DOM02 |  | 2020-05-13 | 11:30 | 12:00 |  | 0:30 | 15:10
Pause |  | 2020-05-13 | 12:10 | 13:00 |  | 0:50 | 16:00
SSD02 |  | 2020-05-13 | 13:00 | 15:00 |  | 2:00 | 18:00
småting |  | 2020-05-13 | 15:00 | 16:00 |  | 1:00 | 19:00
Hjælp af Anders |  | 2020-05-13 | 16:00 | 17:40 |  | 1:40 | 20:40
rettelse af UCD01 efter samtale med Ander |  | 2020-05-14 | 8:30 | 10:00 |  | 1:30 | 22:10
Begynd UC01 |  | 2020-05-14 | 10:00 | 10:45 |  | 0:45 | 22:55
Snak med Anders |  | 2020-05-14 | 10:45 | 12:00 |  | 1:15 | 24:10
Pause |  | 2020-05-14 | 12:00 | 13:00 |  | 1:00 | 25:10
UC01 færdig |  | 2020-05-14 | 13:00 | 14:00 |  | 1:00 | 26:10
AD01 med Toke |  | 2020-05-14 | 14:00 | 14:30 |  | 0:30 | 26:40
DOM01 med MIK |  | 2020-05-14 | 14:30 | 15:30 |  | 1:00 | 27:40
SSD02 |  | 2020-05-14 | 15:30 | 16:30 |  | 1:00 | 28:40
[6 empty] | 0:00 | 28:40
[6 empty] | 0:00 | 28:40
[6 empty] | 0:00 | 28:40
[6 empty] | 0:00 | 28:40

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders