## Ark1
Tidsregistrering af Emil
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Opstart af projekt |  | 2020-05-11 | 8:30 | 11:20 | 2:50 | 2:50 | 0.11806
Udarbejdelse af gruppekontrakt |  | 2020-05-11 | 11:20 | 13:30 | 2:10 | 2:10 | 0.20833
Kravindsamling og UC diagram |  | 2020-05-11 | 14:30 | 16:00 | 1:30 | 1:30 | 0.27083
Diverse projektrelaterede opgaver |  | 2020-05-12 | 8:30 | 9:00 | 0:30 | 0:30 | 0.29167
Lavet mockups til UC01 og UC02 |  | 2020-05-12 | 9:00 | 12:00 | 2:00 | 3:00 | 0.41667
Review af visionsdokument |  | 2020-05-12 | 13:00 | 13:10 | 0:30 | 0:10 | 0.42361
Lavet readme |  | 2020-05-12 | 13:10 | 13:20 | 0:10 | 0:10 | 0.43056
Review af risikoanalyse og rettelser til metrikker |  | 2020-05-12 | 13:25 | 15:00 | 1:00 | 1:35 | 0.49653
Rettet readme |  | 2020-05-12 | 15:00 | 15:10 | 0:05 | 0:10 | 0.50347
Projektplan og gruppemøde |  | 2020-05-12 | 15:30 | 16:30 | 1:30 | 1:00 | 0.54514
Lavet UC01 Åbn beskeder |  | 2020-05-13 | 8:30 | 9:30 | 1:00 | 1:00 | 0.58681
Lavet AD02 Send besked |  | 2020-05-13 | 9:35 | 10:30 | 1:00 | 0:55 | 0.625
Lavet DOM02 Send besked |  | 2020-05-13 | 10:30 | 12:10 | 1:00 | 1:40 | 0.69444
Lavet SSD01 Åbn beskeder |  | 2020-05-13 | 13:00 | 13:25 | 0:10 | 0:25 | 0.71181
Review af SSD02 Send besked |  | 2020-05-13 | 13:25 | 13:50 | 0:10 | 0:25 | 0.72917
Diverse opgaver |  | 2020-05-13 | 13:50 | 16:00 | 1:00 | 2:10 | 0.81944
Vejledning med Anders |  | 2020-05-13 | 16:00 | 17:30 | 0:20 | 1:30 | 0.88194
Lavet UCD01 |  | 2020-05-14 | 8:30 | 9:30 | 1:00 | 1:00 | 0.92361
Startet på rettelse af UC01 |  | 2020-05-14 | 9:30 | 10:30 | 1:00 | 1:00 | 0.96528
Vejledning med Anders |  | 2020-05-14 | 10:30 | 12:00 | 1:00 | 1:30 | 1899-12-31 00:40
Rettelser efter vejledning og mockups |  | 2020-05-14 | 13:00 | 16:30 | 4:00 | 3:30 | 1899-12-31 04:10
ATD01 og ATD02 |  | 2020-05-15 | 8:30 | 9:20 | 1:00 | 0:50 | 1899-12-31 05:00
Lavet iterationsplan #2 |  | 2020-05-15 | 9:30 | 9:50 | 0:10 | 0:20 | 1899-12-31 05:20
Lavet OC02 sendBesked |  | 2020-05-15 | 9:50 | 10:30 | 1:00 | 0:40 | 1899-12-31 06:00
Reviews og revidering af OC01 og OC02 |  | 2020-05-15 | 10:30 | 11:50 | 1:00 | 1:20 | 1899-12-31 07:20
Skrevet rapport |  | 2020-05-15 | 12:30 | 15:00 | 3:00 | 2:30 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
[6 empty] | 0:00 | 1899-12-31 09:50
Formulas:
Timer i alt = SUM(G3:[Aktuelt tidforbrug (i timer)])

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders