## Ark1
Tidsregistrering af Toke
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Opstart af projekt |  | 2020-05-11 | 8:30 | 11:20 |  | 2:50 | 2:50
Gruppekontakten |  | 2020-05-11 | 11:20 | 13:30 |  | 2:10 | 5:00
Kravindsamling |  | 2020-05-11 | 13:30 | 14:30 |  | 1:00 | 6:00
Use Case Diagram |  | 2020-05-11 | 14:30 | 16:00 |  | 1:30 | 7:30
Kommunikation med Anders |  | 2020-05-12 | 8:30 | 9:30 |  | 1:00 | 8:30
Grundopsætning af rapport |  | 2020-05-12 | 9:30 | 11:00 |  | 1:30 | 10:00
Metrikker – bilag |  | 2020-05-12 | 11:00 | 13:00 |  | 2:00 | 12:00
Review risikoanalyse |  | 2020-05-12 | 13:00 | 14:00 |  | 1:00 | 13:00
Projektplan |  | 2020-05-12 | 14:00 | 16:15 |  | 2:15 | 15:15
Metrikker – rapport |  | 2020-05-12 | 16:15 | 17:15 |  | 1:00 | 16:15
UC01 og UC02 frem til SSD |  | 2020-05-13 | 8:30 | 14:00 |  | 5:30 | 21:45
Vejledning fra Andrés |  | 2020-05-13 | 14:00 | 16:00 |  | 2:00 | 23:45
Vejledning fra Anders |  | 2020-05-13 | 16:00 | 17:30 |  | 1:30 | 25:15
Rettelse af UCD01 |  | 2020-05-14 | 8:30 | 9:45 |  | 1:15 | 26:30
Masse omdøbelse af filer |  | 2020-05-14 | 9:45 | 10:15 |  | 0:30 | 27:00
Rettelse af UC02, samt vejledning fa Anders |  | 2020-05-14 | 10:15 | 13:45 |  | 3:30 | 30:30
Rettelse af AD01 |  | 2020-05-14 | 13:45 | 14:30 |  | 0:45 | 31:15
Rettelse af DOM02 |  | 2020-05-14 | 14:30 | 15:30 |  | 1:00 | 32:15
Rettelse af SSD01 |  | 2020-05-14 | 15:30 | 16:30 |  | 1:00 | 33:15
ATD01+02 |  | 2020-05-15 | 8:30 | 9:15 |  | 0:45 | 34:00
OC0101+0102 |  | 2020-05-15 | 9:15 | 13:00 |  | 3:45 | 37:45
Rapport – Finansiering |  | 2020-05-15 | 13:00 | 16:00 |  | 3:00 | 40:45
SD02+DCD02 |  | 2020-05-15 | 8:30 | 13:00 |  | 4:30 | 45:15
Kunden møde |  | 2020-05-15 | 13:00 | 14:30 |  | 1:30 | 46:45
SD02+DCD02 |  | 2020-05-15 | 14:30 | 16:30 |  | 2:00 | 48:45
[6 empty] | 0:00 | 48:45
[6 empty] | 0:00 | 48:45
[6 empty] | 0:00 | 48:45
[6 empty] | 0:00 | 48:45
[6 empty] | 0:00 | 48:45

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders