## Ark1
Tidsregistrering af (Navn)
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Opstart af projekt |  | 2020-05-11 | 8:30 | 11:20 | 2:50 | 2:50 | 2:50
Udarbejdelse af gruppekontrakt |  | 2020-05-11 | 11:20 | 13:30 | 2:10 | 2:10 | 5:00
Kravindsamling og UC diagram |  | 2020-05-11 | 14:30 | 16:00 | 1:30 | 1:30 | 6:30
Diverse projektrelaterede opgaver |  | 2020-05-12 | 8:30 | 9:00 | 0:30 | 0:30 | 7:00
Lavet mockups til UC01 og UC02 |  | 2020-05-12 | 9:00 | 12:00 | 2:00 | 3:00 | 10:00
Review af visionsdokument |  | 2020-05-12 | 13:00 | 13:10 | 0:30 | 0:10 | 10:10
Lavet readme |  | 2020-05-12 | 13:10 | 13:20 | 0:10 | 0:10 | 10:20
Review af risikoanalyse og rettelser til metrikker |  | 2020-05-12 | 13:25 | 15:00 | 1:00 | 1:35 | 11:55
Rettet readme |  | 2020-05-12 | 15:00 | 15:10 | 0:05 | 0:10 | 12:05
Projektplan og gruppemøde |  | 2020-05-12 | 15:30 | 16:30 | 1:30 | 1:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05
[6 empty] | 0:00 | 13:05

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders